## Phase_Task_Breakdown
Phase | Task Description | Subtasks | Total Hours
A. Project Kickoff & Setup | A.1 Data Ingestion – Load customers.csv, events.csv, offers.csv into Power BI Desktop import data_dictionary.csv for reference. | Verify encoding and delimiters Load and preview each table Rename columns as needed (remove spaces/special chars) Ensure relationships between offer_id and customer_id fields. | 10
B. Data Transformation & Cleaning | B.1 Parse Events Data – Extract offer_id and transaction amount from events.value JSON pivot event types. | Use Power Query to parse JSON in events.value Create columns: offer_id, transaction_amount Pivot events into columns (received, viewed, completed, transaction) by customer and offer Handle missing values. | 15
B. Data Transformation & Cleaning | B.2 Clean Customer & Offer Tables – Standardize demographics and offer metadata. | Convert became_member_on to date Handle missing gender and income Split channels into separate rows or columns Standardize offer_type and difficulty fields. | 10
C. Data Modeling & Relationships | C.1 Build Data Model – Customer and Offer dimension tables, and a fact table for CustomerOfferEvents. | Create Customer dimension (customer_id, demographics) Offer dimension (offer_id, type, difficulty, reward, duration, channels) Create fact table by merging parsed events with customer and offer tables Establish relationships. | 15
D. DAX Calculations & Measures | D.1 Basic Engagement Measures – Total offers sent, viewed, completed, redemption rate, total transaction count and amount. | Define TotalOffersSent = COUNT of offer received events TotalOffersViewed = COUNT of offer viewed TotalOffersCompleted = COUNT of offer completed RedemptionRate = DIVIDE(TotalOffersCompleted, TotalOffersSent) TotalTransactions = SUM of transaction_amount AverageTransaction = AVERAGE of transaction_amount. | 15
E. Segmentation & Cohort Analysis | E.1 Customer Segmentation – Create demographic cohorts and engagement levels. | Define age groups, income brackets, tenure cohorts Compute engagement type (e.g., high viewer, high completer) Create measures for average redemption per cohort Build DAX for cohort-specific metrics. | 20
F. Visualization & UX Design | F.1 Build Core Report Pages – Overview, Offer Funnel, Customer Segmentation, Offer Performance, Transaction Behavior. | Page 1: KPIs and overall trends Page 2: Funnel visualization from received to transaction Page 3: Demographic segmentation charts Page 4: Offer performance by type, channel, difficulty Page 5: Transaction time-based analysis. | 35
F. Visualization & UX Design | F.2 Enhance Interactivity & Custom Features – Drill-through, custom tooltips, dynamic slicers. | Add drill-through from offer to customer details Create tooltips showing customer demographics and engagement Configure slicers for age groups, channels, offer types Add bookmarks for scenario snapshots. | 10
G. Testing, QA & Optimization | G.1 DAX Validation & Data Accuracy – Verify DAX measures against raw data for sample customers/offers. | Randomly sample 50 customers to validate engagement counts Check JSON parsing accuracy Confirm redemption rates with manual calculations in Excel Validate relationship cardinalities. | 10
G. Testing, QA & Optimization | G.2 Performance Tuning – Optimize data model and visuals. | Remove unused columns Aggregate tables where possible Simplify complex DAX Limit visual data points (e.g., top N filters) Verify dashboard refresh time (<3 minutes). | 5
H. Documentation & Deployment | H.1 User Guide & Technical Documentation – Document data model, DAX formulas, Power Query steps. | User Guide: How to refresh data, use each page, adjust slicers Technical Doc: ERD diagram, DAX code snippets, M code for JSON parsing, instructions for adding new offers. | 10
H. Documentation & Deployment | H.2 Publish to Power BI Service – Upload .pbix, set permissions, schedule refresh. | Upload .pbix to workspace Assign Viewer/Editor roles Configure scheduled refresh schedule Share link with marketing team stakeholders.
I. Team Coordination & Meetings | I.1 Sprint Planning & Stand-ups – Kickoff, weekly stand-ups, mid-sprint review, final demo, retrospective. | Kickoff (2h) Weekly stand-ups (1.5h) Mid-sprint review (2h) Final demo (2h) Retrospective (2.5h). | 10

## Effort_Allocation
Learner | Assignments | Total Hours
L1 | A.1 Data Ingestion (10 h) B.2 Customer & Offer Cleaning (5 h) C.1 Data Model Setup (5 h) D.1 Basic Measures (5 h) H.1 User Guide (3 h) I.1 Coordination (2 h) | 30
L2 | B.1 Event Parsing (10 h) C.1 Data Model Setup (5 h) D.1 Basic Measures (5 h) F.1 Overview & Funnel visuals (8 h) I.1 Coordination (2 h) | 30
L3 | C.1 Data Model Setup (5 h) D.1 Basic Measures (5 h) E.1 Segmentation & Cohorts (10 h) F.1 Segmentation visuals (5 h) G.1 DAX Validation (3 h) I.1 Coordination (2 h) | 30
L4 | E.1 Segmentation & Cohorts (10 h) F.1 Offer Performance visuals (10 h) F.2 Interactivity & Tooltips (5 h) G.2 Tuning (3 h) I.1 Coordination (2 h) | 30
L5 | B.2 Customer & Offer Cleaning (5 h) F.1 Transaction Behavior visuals (10 h) G.1 DAX Validation (7 h) H.1 Technical Doc (3 h) I.1 Coordination (2 h) | 27

## Timeline
Week | Milestone/Deliverables
Week 1 | Kickoff: L1 imports data B.1 Event Parsing: L2 parses JSON B.2 Cleaning: L1, L5 standardize customers and offers C.1 Initial Data Model: L1, L2, L3 set up dimensions and fact table.
Week 2 | DAX Measures: L1, L2, L3 create engagement and basic metrics E.1 Segmentation: L3, L4 build cohorts and metrics F.1 UI Skeleton: L2, L3, L4, L5 draft Overview, Funnel, Segmentation pages.
Week 3 | Visualization Refinement: L2, L3, L4, L5 finalize all pages & interactivity G.1 & G.2 Testing & QA: L2, L3, L4, L5 validate DAX, optimize model Documentation & Publish: L1, L5 finalize guides publish to Power BI Service Final demo & retrospective.

## Key_Deliverables
Deliverable | Details
Parsed & Cleaned Tables | Event table parsed into event types with offer_id and transaction_amount Customer and Offer tables standardized.
Star Schema Data Model | Relationships linking Customer and Offer dimensions to CustomerOfferEvents fact table.
DAX Measures | Engagement metrics: TotalOffersSent, TotalOffersViewed, TotalOffersCompleted, RedemptionRate Transaction metrics: TotalTransactions, AverageTransaction.
Segmentation Metrics | Cohort definitions by age, gender, income, engagement Measures for cohort-specific redemption and spend.
Power BI .pbix Report | Pages: Overview, Offer Funnel, Customer Segmentation, Offer Performance, Transaction Behavior with interactivity.
Documentation | User Guide and Technical Documentation with data model, DAX, M code, and usage instructions.
Published Workspace | .pbix uploaded to Power BI Service, permissions set, scheduled refresh configured, link shared with stakeholders.

## How_to_Use_Plan
Step | Details
Sprint Kickoff (Day 1) | L1 imports data, verifies schema review plan, assign roles set up shared folder with CSVs and project docs.
Daily Stand-ups | Each learner reports progress, plans, and blockers update project board.
Mid-Sprint Review (End of Week 2) | Demo data model, DAX metrics, segmentation approaches, initial visuals collect feedback.
Final Demo & Handover (End of Week 3) | Present full dashboard walk through documentation publish to Power BI Service confirm scheduled refresh.
Retrospective | Discuss successes, challenges, and lessons document improvements for future iterations.